## coolwater
COOLWATER
Sign Off Date | 2021-02-08 |  |  | CESAR | CESAR | CESAR | CESAR | CESAR | EVAN | Cesar | Cesar | Cesar | Cesar | Tony | Tony | Cesar | Tony | Michael | Tony | Michael | TONY | Chris/Evan | Tony | Michael | Michael | Michael | Tony | Michael | Michael | Michael
Job Due Date | 2021-07-12 |  |  | Identify | Identify | Identify | Complete | Order Outside Machining | Procure Trim | Identify All | Cut/Kit Fixed & | Order All | Cut/Machine/Kit | Screen Fab | All Fixed Units | Confirm Glass 100% | Kanban Units | Patina Thresholds/C-Bolts | Machined Units | Screens Meshed | Pick up | Ensure Totes 100% | Pick up Kanban | Fixed Units | Install All | All Kanban | Pick up "Machined" | All Kanban | All Machined | All Machined
5 Month Lead Time | 2021-07-08 |  |  | Fixed Units | KANBAN Units | Machined Units | BOM By Unit | (kickplate/lockbox/etc) | Hardware + "Specials" | Units w/ Screens | Kanban Units | Glass | Remaining Units | Complete | To Finish |  | Fab'd - Delivered to Finish | Strikes Provide to Chris | Delivered to Finish | & Packaged | Matson/Galv/Met Fixed |  | From Finish | Glazed/Complete | Fixed Units | Glazed | From Finish | Installed | Glazed | Installed
|  |  |  | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-02-18 | 2021-02-18 | 2021-02-22 | 2021-02-22 | 2021-03-08 | 2021-04-05 | 2021-04-05 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-05-24 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-06-14 | 2021-06-14 | 2021-06-28
|  |  |  | FIXED | KANBAN | MACHINED | Completion Date/NA | Completion Date | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA
COOLWATER | D106B | Breakfast Porch 105 | 4 Panel Slider w/ Pockets (PXX-XXP) |  |  | machined |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | D128A | Bed 1 | Swing Door Pair |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | D134A | Master Bed | Swing Door Pair |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | D140A | Bed 2 | Swing Door Pair |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | D122A | Staff Room | Swing Door Pair |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | D115 | Staff Room | Casement Pair |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | D122D | Staff Room | Swing Door Pair |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | D117 | Staff Room | Casement Pair |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | D102A | Gym 102 | Swing Door Pair |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | D101A | Gym 102 | Swing Door Pair |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | W107 | Gym 102 | Fixed Window | Fixed | [5 empty] | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | W108 | Gym 102 | Fixed Window | Fixed | [5 empty] | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | W109 | Gym 102 | Fixed Window | Fixed | [5 empty] | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | W110 | Gym 102 | Fixed Window | Fixed | [5 empty] | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | W111 | Gym 102 | Fixed Window | Fixed | [5 empty] | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | W112 | Gym 102 | Fixed Window | Fixed | [5 empty] | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | W113 | Gym 102 | Fixed Window | Fixed | [5 empty] | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | W114 | Gym 102 | Fixed Window | Fixed | [5 empty] | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | W15 | Gym 102 | Fixed Window | Fixed | [5 empty] | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | W16 | Gym 102 | Fixed Window | Fixed | [5 empty] | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
COOLWATER | W17 | Gym 102 | Fixed Window | Fixed
COOLWATER | W18 | Gym 102 | Fixed Window | Fixed
COOLWATER | W19 | Gym 102 | Fixed Window | Fixed
COOLWATER | W20 | Gym 102 | Fixed Window | Fixed
COOLWATER | W115 | Bed 109 | Casement Pair |  | Kanban
COOLWATER | W116 | Bed 111 | Casement Pair |  | Kanban
COOLWATER | W117 | Bed 111 | Casement Pair |  | Kanban
COOLWATER | W117.1 | Bed 109 | Casement Pair |  | Kanban
COOLWATER | D111B | Bed 111 | Swing Door Pair |  | Kanban
COOLWATER | W118 | Not Given | Fixed Diamond | Fixed
COOLWATER | W118.1 | Not Given | Fixed Diamond | Fixed
COOLWATER | W118.2 | Not Given | Fixed Diamond | Fixed
COOLWATER | W118.3 | Bath 110 | Fixed Diamond | Fixed
COOLWATER | D109B | Bed 109 | Swing Door Pair |  | Kanban
COOLWATER | W119 | Bath 112 | Fixed Diamond | Fixed
COOLWATER | W125 | Kitchen | Fixed | Fixed
COOLWATER | W126 | Kitchen | Casement Pair |  | Kanban
COOLWATER | W127 | Kitchen | Fixed | Fixed
COOLWATER | W128 | Library | Triple Casement |  | Kanban

## EVR
EVR
Sign Off Date | 2021-02-25 |  |  |  | CESAR | CESAR | CESAR | CESAR | CESAR | EVAN | Cesar | Cesar | Cesar | Cesar | Tony | Tony | Cesar | Tony | Michael | Tony | Michael | TONY | Chris/Evan | Tony | Michael | Michael | Michael | Tony | Michael | Michael | Michael
Job Due Date | 2021-07-29 |  |  |  | Identify | Identify | Identify | Complete | Order Outside Machining | Procure Trim | Identify All | Cut/Kit Fixed & | Order All | Cut/Machine/Kit | Screen Fab | All Fixed Units | Confirm Glass 100% | Kanban Units | Patina Thresholds/C-Bolts | Machined Units | Screens Meshed | Pick up | Ensure Totes 100% | Pick up Kanban | Fixed Units | Install All | All Kanban | Pick up "Machined" | All Kanban | All Machined | All Machined
5 Month Lead Time | 2021-07-25 |  |  |  | Fixed Units | KANBAN Units | Machined Units | BOM By Unit | (kickplate/lockbox/etc) | Hardware + "Specials" | Units w/ Screens | Kanban Units | Glass | Remaining Units | Complete | To Finish |  | Fab'd - Delivered to Finish | Strikes Provide to Chris | Delivered to Finish | & Packaged | Matson/Galv/Met Fixed |  | From Finish | Glazed/Complete | Fixed Units | Glazed | From Finish | Installed | Glazed | Installed
[5 empty] | 2021-02-25 | 2021-02-25 | 2021-02-25 | 2021-02-25 | 2021-02-25 | 2021-03-07 | 2021-03-07 | 2021-03-11 | 2021-03-11 | 2021-03-25 | 2021-04-22 | 2021-04-22 | 2021-05-06 | 2021-05-13 | 2021-05-20 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-06-10 | 2021-06-17 | 2021-06-17 | 2021-06-17 | 2021-07-01 | 2021-07-01 | 2021-07-15
[5 empty] | FIXED | KANBAN | MACHINED | Completion Date/NA | Completion Date | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA
EVR | 113.1 | Kitchen 113 | Casement Pair w/ Sidelites | 37 |  |  | machined |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 115A | Family Room 115 | Swing Pair Door | 78 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 115B | Family Room 115 | 4 Panel Slider (OXXX) | 120 |  |  | machined |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 115C | Family Room 115 | 4 Panel Slider (OXXX) | 120 |  |  | machined |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 115D | Family Room 115 | 4 Panel Slider (XXXO) | 120 |  |  | machined |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 115E | Family Room 115 | Swing Pair Door | 78 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 121A | Living 121 | 6 Panel Slider (OXX-XXO) | 207 |  |  | machined |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 121B | Living 121 | 6 Panel Slider (OXX-XXO) | 187 |  |  | machined |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 146A | Green Room 146 | Swing Pair Door | 50 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 212.1.1 | Bath 212.1 | Single Casement | 8 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 212.2.1 | Closet 212.2 | Single Casement | 8 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 244.1 | Bedroom 244 | Casement Pair w/ Sidelites | 25 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 244.2 | Bedroom 244 | Casement Pair w/ Sidelites | 25 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 244.3 | Bedroom 244 | Casement Pair w/ Sidelites | 25 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 248.1 | Corridor 248 | Casement Pair w/ Sidelites | 25 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 248.2 | Corridor 248 | Casement Pair w/ Sidelites | 26 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 248.3 | Corridor 248 | Casement Pair w/ Sidelites | 27 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 211A | Play Deck 211 | Swing Pair Door | 50 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 211B | Play Deck 211 | Swing Pair Door | 50 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA
EVR | 248A | Guest Suite Hallway | Single Swing Door w/ Sidelite | 24 |  | Kanban |  |  |  |  | NA |  |  |  | NA | NA |  |  |  |  | NA | NA |  |  | NA | NA

## Graulich
GRAULICH
Sign Off Date | 2020-12-01 |  |  |  | CESAR | CESAR | CESAR | CESAR | CESAR | EVAN | Cesar | Cesar | Cesar | Cesar | Tony | Tony | Cesar | Tony | Michael | Tony | Michael | TONY | Chris/Evan | Tony | Michael | Michael | Michael | Tony | Michael | Michael | Michael
Job Due Date | 2021-05-04 |  |  |  | Identify | Identify | Identify | Complete | Order Outside Machining | Procure Trim | Identify All | Cut/Kit Fixed & | Order All | Cut/Machine/Kit | Screen Fab | All Fixed Units | Confirm Glass 100% | Kanban Units | Patina Thresholds/C-Bolts | Machined Units | Screens Meshed | Pick up | Ensure Totes 100% | Pick up Kanban | Fixed Units | Install All | All Kanban | Pick up "Machined" | All Kanban | All Machined | All Machined
5 Month Lead Time | 2021-04-30 |  |  |  | Fixed Units | KANBAN Units | Machined Units | BOM By Unit | (kickplate/lockbox/etc) | Hardware + "Specials" | Units w/ Screens | Kanban Units | Glass | Remaining Units | Complete | To Finish |  | Fab'd - Delivered to Finish | Strikes Provide to Chris | Delivered to Finish | & Packaged | Matson/Galv/Met Fixed |  | From Finish | Glazed/Complete | Fixed Units | Glazed | From Finish | Installed | Glazed | Installed
[5 empty] | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-11 | 2020-12-11 | 2020-12-15 | 2020-12-15 | 2020-12-29 | 2021-01-26 | 2021-01-26 | 2021-02-09 | 2021-02-16 | 2021-02-23 | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2021-03-16 | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2021-04-06 | 2021-04-06 | 2021-04-20
[5 empty] | FIXED | KANBAN | MACHINED | Completion Date/NA | Completion Date | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA
GRAULICH | D7 | Rec Room | 6 Panel Pocket Slider (PXXX-XXXP) | 270 |  |  | Machined
GRAULICH | W7 | Bath #1 | Casement | 6 |  | Kanban
GRAULICH | W57 | Guest Bath | Casement | 9 |  | Kanban
GRAULICH | W56 | Guest Bedroom | Casement | 9 |  | Kanban
GRAULICH | W55 | Guest Bedroom | Casement | 9 |  | Kanban
GRAULICH | W26 | Guest Shower | Casement | 3 |  | Kanban
GRAULICH | W22 | Powder | Casement | 8 |  | Kanban
GRAULICH | W11 | Max's Bedroom | Casement | 6 |  | Kanban
GRAULICH | W39 | Kitchen | Casement / Fixed / Casement | 77 |  | Kanban
GRAULICH | W8 | Max's Bedroom | Casement Over Fixed | 12 |  | Kanban
GRAULICH | W6 | Eli's Bedroom | Casement Over Fixed | 12 |  | Kanban
GRAULICH | W5 | Eli's Bedroom | Casement Over Fixed | 12 |  | Kanban
GRAULICH | W2 | Fay's Bedroom | Casement Over Fixed | 12 |  | Kanban
GRAULICH | W28 | Master Bath | Casement PAIR Over Fixed | 21 |  | Kanban
GRAULICH | W9 | Max's Bedroom | Fixed | 12 | Fixed
GRAULICH | W64 | Guest Living/Dining | Fixed | 24 | Fixed
GRAULICH | W63 | Guest Kitchen | Fixed | 6 | Fixed
GRAULICH | W61 | Guest Closet | Fixed | 4 | Fixed
GRAULICH | W60 | Guest Bath | Fixed | 9 | Fixed
GRAULICH | W59 | Guest Bath | Fixed | 9 | Fixed
GRAULICH | W58 | Guest Bath | Fixed | 9 | Fixed
GRAULICH | W53 | Garage | Fixed | 9 | Fixed
GRAULICH | W52 | Garage | Fixed | 9 | Fixed
GRAULICH | W51 | Entry Hall | Fixed | 11 | Fixed
GRAULICH | W50 | Entry Hall | Fixed | 42 | Fixed
GRAULICH | W49 | Living/Dining | Fixed | 53 | Fixed
GRAULICH | W48 | Mud Room | Fixed | 11 | Fixed
GRAULICH | W46 | Mud Room | Fixed | 11 | Fixed
GRAULICH | W44 | Mud Room | Fixed | 11 | Fixed
GRAULICH | W40 | Kitchen | Fixed | 9 | Fixed
GRAULICH | W4 | Fay's Bedroom | Fixed | 12 | Fixed
GRAULICH | W38 | Kitchen | Fixed | 9 | Fixed
GRAULICH | W37 | Living/Dining | Fixed | 47 | Fixed
GRAULICH | W32 | Master Bedroom | Fixed | 21 | Fixed
GRAULICH | W31 | Master Bedroom | Fixed | 21 | Fixed
GRAULICH | W3 | Fay's Bedroom | Fixed | 12 | Fixed
GRAULICH | W29 | Master Bedroom | Fixed | 21 | Fixed
GRAULICH | W27 | Master Bath | Fixed | 77 | Fixed
GRAULICH | W25 | Guest Bath | Fixed | 8 | Fixed
GRAULICH | W23 | Library/Guest | Fixed | 13 | Fixed
GRAULICH | W21 | Coat | Fixed | 11 | Fixed
GRAULICH | W19 | Entry | Fixed | 11 | Fixed
GRAULICH | W14 | Rec Room | Fixed | 48 | Fixed
GRAULICH | W10 | Max's Bedroom | Fixed | 12 | Fixed
GRAULICH | W47 | Mud Room | Fixed w/ Hopper Below | 11 |  | Kanban
GRAULICH | W45 | Mud Room | Fixed w/ Hopper Below | 11 |  | Kanban
GRAULICH | W20 | Fountain Pool | Fixed w/ Hopper Below | 11 |  | Kanban
GRAULICH | W65 | Guest Living/Dining | Fixed w/ Single Casement | 24 |  | Kanban
GRAULICH | W36 | Stair Hall | Fixed w/ Single Casement | 137 |  | Kanban
GRAULICH | W1 | Fay's Bath | Fixed w/ Single Casement | 39 |  | Kanban
GRAULICH | W62 | Guest Kitchen | Hopper | 9 |  | Kanban
GRAULICH | W43 | Kitchen Powder | Hopper | 6 |  | Kanban
GRAULICH | W42 | Laundry | Hopper | 16 |  | Kanban
GRAULICH | W41 | Pantry | Hopper | 16 |  | Kanban
GRAULICH | W13 | Courtyard Stairs | Hopper | 3 |  | Kanban
GRAULICH | W12 | Pool Bath | Hopper | 3 |  | Kanban
GRAULICH | D14 | Master Bedroom | Inswing Casement Pair | 24 |  | Kanban
GRAULICH | D13 | Master Bedroom | Inswing Casement Pair | 24 |  | Kanban
GRAULICH | D12 | Master Bedroom | Inswing Casement Pair | 24 |  | Kanban
GRAULICH | D11 | Master Bedroom | Inswing Casement Pair | 48 |  | Kanban
GRAULICH | W24 | Library/Guest | Inswing Casement Over Fixed | 11 |  | Kanban
GRAULICH | W33 | Master Bedroom | Inswing Casement Pair Over Fixed | 21 |  | Kanban
GRAULICH | W30 | Master Bedroom | Inswing Casement Pair Over Fixed | 21 |  | Kanban
GRAULICH | D4 | Hall | Swing Door | 21 |  |  | Machined
GRAULICH | D20 | Pantry | Swing Door | 21 |  |  | Machined
GRAULICH | D1 | Fay's Bedroom | Swing Door Pair | 28 |  |  | Machined
GRAULICH | D6 | Courtyard | Swing Door Pair | 54 |  |  | Machined
GRAULICH | D5 | Courtyard | Swing Door Pair | 28 |  |  | Machined
GRAULICH | D3 | Max's Bedroom | Swing Door Pair | 28 |  |  | Machined
GRAULICH | D25 | Guest Bedroom | Swing Door Pair | 28 |  |  | Machined
GRAULICH | D2 | Eli's Bedroom | Swing Door Pair | 28 |  |  | Machined
GRAULICH | D19 | Kitchen | Swing Door Pair | 38 |  |  | Machined
GRAULICH | D15 | Master Bedroom | Swing Door Pair | 24 |  |  | Machined
GRAULICH | D26 | Guest Living/Dining | Swing Door Pair w/ Fixed Sidelites | 68 |  |  | Machined
GRAULICH | D18 | Living/Dining | Swing Door Pair w/ Fixed Sidelites | 84 |  |  | Machined
GRAULICH | D17 | Living/Dining | Swing Door Pair w/ Fixed Sidelites | 84 |  |  | Machined
GRAULICH | D16 | Living/Dining | Swing Door Pair w/ Fixed Sidelites | 84 |  |  | Machined

## REYNOLDS
REYNOLDS
Sign Off Date | 2021-02-05 |  |  |  | CESAR | CESAR | CESAR | CESAR | CESAR | EVAN | Cesar | Cesar | Cesar | Cesar | Tony | Tony | Cesar | Tony | Michael | Tony | Michael | TONY | Chris/Evan | Tony | Michael | Michael | Michael | Tony | Michael | Michael | Michael
Job Due Date | 2021-07-09 |  |  |  | Identify | Identify | Identify | Complete | Order Outside Machining | Procure Trim | Identify All | Cut/Kit Fixed & | Order All | Cut/Machine/Kit | Screen Fab | All Fixed Units | Confirm Glass 100% | Kanban Units | Patina Thresholds/C-Bolts | Machined Units | Screens Meshed | Pick up | Ensure Totes 100% | Pick up Kanban | Fixed Units | Install All | All Kanban | Pick up "Machined" | All Kanban | All Machined | All Machined
5 Month Lead Time | 2021-07-05 |  |  |  | Fixed Units | KANBAN Units | Machined Units | BOM By Unit | (kickplate/lockbox/etc) | Hardware + "Specials" | Units w/ Screens | Kanban Units | Glass | Remaining Units | Complete | To Finish |  | Fab'd - Delivered to Finish | Strikes Provide to Chris | Delivered to Finish | & Packaged | Matson/Galv/Met Fixed |  | From Finish | Glazed/Complete | Fixed Units | Glazed | From Finish | Installed | Glazed | Installed
[5 empty] | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-02-15 | 2021-02-15 | 2021-02-19 | 2021-02-19 | 2021-03-05 | 2021-04-02 | 2021-04-02 | 2021-04-16 | 2021-04-23 | 2021-04-30 | 2021-05-07 | 2021-05-07 | 2021-05-07 | 2021-05-07 | 2021-05-07 | 2021-05-21 | 2021-05-28 | 2021-05-28 | 2021-05-28 | 2021-06-11 | 2021-06-11 | 2021-06-25
[5 empty] | FIXED | KANBAN | MACHINED | Completion Date/NA | Completion Date | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA
REYNOLDS | X100.1 | Entry | Single Swing Door w/ Fixed Sidelites & Arched Transomn | 40 |  | Kanban
REYNOLDS | X103.1 | Library | Fixed Oval w/ Leaded Glass | 32 | Fixed
REYNOLDS | X103.2 | Library | Fixed Oval w/ Leaded Glass | 32 | Fixed
REYNOLDS | X105.1 | Loggia | Swing Door Pair w/ fixed Sidlites & Transom | 156 |  | Kanban
REYNOLDS | X105.2 | Loggia | Swing Door Pair w/ fixed Sidlites & Transom | 156 |  | Kanban
REYNOLDS | X180.2 | Connector | Single Swing Door w/ Fixed Sidelites | 73 |  | Kanban
REYNOLDS | X501.1 | Guest Living | Single Swing Door w/ Fixed Surround | 128 |  | Kanban

## Chartwell
CHARTWELL
Sign Off Date | 2020-12-01 |  |  |  | CESAR | CESAR | CESAR | CESAR | CESAR | EVAN | Cesar | Cesar | Cesar | Cesar | Tony | Tony | Cesar | Tony | Michael | Tony | Michael | TONY | Chris/Evan | Tony | Michael | Michael | Michael | Tony | Michael | Michael | Michael
Job Due Date | 2021-05-04 |  |  |  | Identify | Identify | Identify | Complete | Order Outside Machining | Procure Trim | Identify All | Cut/Kit Fixed & | Order All | Cut/Machine/Kit | Screen Fab | All Fixed Units | Confirm Glass 100% | Kanban Units | Patina Thresholds/C-Bolts | Machined Units | Screens Meshed | Pick up | Ensure Totes 100% | Pick up Kanban | Fixed Units | Install All | All Kanban | Pick up "Machined" | All Kanban | All Machined | All Machined
5 Month Lead Time | 2021-04-30 |  |  |  | Fixed Units | KANBAN Units | Machined Units | BOM By Unit | (kickplate/lockbox/etc) | Hardware + "Specials" | Units w/ Screens | Kanban Units | Glass | Remaining Units | Complete | To Finish |  | Fab'd - Delivered to Finish | Strikes Provide to Chris | Delivered to Finish | & Packaged | Matson/Galv/Met Fixed |  | From Finish | Glazed/Complete | Fixed Units | Glazed | From Finish | Installed | Glazed | Installed
[5 empty] | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-11 | 2020-12-11 | 2020-12-15 | 2020-12-15 | 2020-12-29 | 2021-01-26 | 2021-01-26 | 2021-02-09 | 2021-02-16 | 2021-02-23 | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2021-03-16 | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2021-04-06 | 2021-04-06 | 2021-04-20
[5 empty] | FIXED | KANBAN | MACHINED | Completion Date/NA | Completion Date | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA | Completion Date/NA
GRAULICH | D7 | Rec Room | 6 Panel Pocket Slider (PXXX-XXXP) | 270 |  |  | Machined
GRAULICH | W7 | Bath #1 | Casement | 6 |  | Kanban
GRAULICH | W57 | Guest Bath | Casement | 9 |  | Kanban
GRAULICH | W56 | Guest Bedroom | Casement | 9 |  | Kanban
GRAULICH | W55 | Guest Bedroom | Casement | 9 |  | Kanban
GRAULICH | W26 | Guest Shower | Casement | 3 |  | Kanban
GRAULICH | W22 | Powder | Casement | 8 |  | Kanban
GRAULICH | W11 | Max's Bedroom | Casement | 6 |  | Kanban
GRAULICH | W39 | Kitchen | Casement / Fixed / Casement | 77 |  | Kanban
GRAULICH | W8 | Max's Bedroom | Casement Over Fixed | 12 |  | Kanban
GRAULICH | W6 | Eli's Bedroom | Casement Over Fixed | 12 |  | Kanban
GRAULICH | W5 | Eli's Bedroom | Casement Over Fixed | 12 |  | Kanban
GRAULICH | W2 | Fay's Bedroom | Casement Over Fixed | 12 |  | Kanban
GRAULICH | W28 | Master Bath | Casement PAIR Over Fixed | 21 |  | Kanban
GRAULICH | W9 | Max's Bedroom | Fixed | 12 | Fixed
GRAULICH | W64 | Guest Living/Dining | Fixed | 24 | Fixed
GRAULICH | W63 | Guest Kitchen | Fixed | 6 | Fixed
GRAULICH | W61 | Guest Closet | Fixed | 4 | Fixed
GRAULICH | W60 | Guest Bath | Fixed | 9 | Fixed
GRAULICH | W59 | Guest Bath | Fixed | 9 | Fixed
GRAULICH | W58 | Guest Bath | Fixed | 9 | Fixed
GRAULICH | W53 | Garage | Fixed | 9 | Fixed
GRAULICH | W52 | Garage | Fixed | 9 | Fixed
GRAULICH | W51 | Entry Hall | Fixed | 11 | Fixed
GRAULICH | W50 | Entry Hall | Fixed | 42 | Fixed
GRAULICH | W49 | Living/Dining | Fixed | 53 | Fixed
GRAULICH | W48 | Mud Room | Fixed | 11 | Fixed
GRAULICH | W46 | Mud Room | Fixed | 11 | Fixed
GRAULICH | W44 | Mud Room | Fixed | 11 | Fixed
GRAULICH | W40 | Kitchen | Fixed | 9 | Fixed
GRAULICH | W4 | Fay's Bedroom | Fixed | 12 | Fixed
GRAULICH | W38 | Kitchen | Fixed | 9 | Fixed
GRAULICH | W37 | Living/Dining | Fixed | 47 | Fixed
GRAULICH | W32 | Master Bedroom | Fixed | 21 | Fixed
GRAULICH | W31 | Master Bedroom | Fixed | 21 | Fixed
GRAULICH | W3 | Fay's Bedroom | Fixed | 12 | Fixed
GRAULICH | W29 | Master Bedroom | Fixed | 21 | Fixed
GRAULICH | W27 | Master Bath | Fixed | 77 | Fixed
GRAULICH | W25 | Guest Bath | Fixed | 8 | Fixed
GRAULICH | W23 | Library/Guest | Fixed | 13 | Fixed
GRAULICH | W21 | Coat | Fixed | 11 | Fixed
GRAULICH | W19 | Entry | Fixed | 11 | Fixed
GRAULICH | W14 | Rec Room | Fixed | 48 | Fixed
GRAULICH | W10 | Max's Bedroom | Fixed | 12 | Fixed
GRAULICH | W47 | Mud Room | Fixed w/ Hopper Below | 11 |  | Kanban
GRAULICH | W45 | Mud Room | Fixed w/ Hopper Below | 11 |  | Kanban
GRAULICH | W20 | Fountain Pool | Fixed w/ Hopper Below | 11 |  | Kanban
GRAULICH | W65 | Guest Living/Dining | Fixed w/ Single Casement | 24 |  | Kanban
GRAULICH | W36 | Stair Hall | Fixed w/ Single Casement | 137 |  | Kanban
GRAULICH | W1 | Fay's Bath | Fixed w/ Single Casement | 39 |  | Kanban
GRAULICH | W62 | Guest Kitchen | Hopper | 9 |  | Kanban
GRAULICH | W43 | Kitchen Powder | Hopper | 6 |  | Kanban
GRAULICH | W42 | Laundry | Hopper | 16 |  | Kanban
GRAULICH | W41 | Pantry | Hopper | 16 |  | Kanban
GRAULICH | W13 | Courtyard Stairs | Hopper | 3 |  | Kanban
GRAULICH | W12 | Pool Bath | Hopper | 3 |  | Kanban
GRAULICH | D14 | Master Bedroom | Inswing Casement Pair | 24 |  | Kanban
GRAULICH | D13 | Master Bedroom | Inswing Casement Pair | 24 |  | Kanban
GRAULICH | D12 | Master Bedroom | Inswing Casement Pair | 24 |  | Kanban
GRAULICH | D11 | Master Bedroom | Inswing Casement Pair | 48 |  | Kanban
GRAULICH | W24 | Library/Guest | Inswing Casement Over Fixed | 11 |  | Kanban
GRAULICH | W33 | Master Bedroom | Inswing Casement Pair Over Fixed | 21 |  | Kanban
GRAULICH | W30 | Master Bedroom | Inswing Casement Pair Over Fixed | 21 |  | Kanban
GRAULICH | D4 | Hall | Swing Door | 21 |  |  | Machined
GRAULICH | D20 | Pantry | Swing Door | 21 |  |  | Machined
GRAULICH | D1 | Fay's Bedroom | Swing Door Pair | 28 |  |  | Machined
GRAULICH | D6 | Courtyard | Swing Door Pair | 54 |  |  | Machined
GRAULICH | D5 | Courtyard | Swing Door Pair | 28 |  |  | Machined
GRAULICH | D3 | Max's Bedroom | Swing Door Pair | 28 |  |  | Machined
GRAULICH | D25 | Guest Bedroom | Swing Door Pair | 28 |  |  | Machined
GRAULICH | D2 | Eli's Bedroom | Swing Door Pair | 28 |  |  | Machined
GRAULICH | D19 | Kitchen | Swing Door Pair | 38 |  |  | Machined
GRAULICH | D15 | Master Bedroom | Swing Door Pair | 24 |  |  | Machined
GRAULICH | D26 | Guest Living/Dining | Swing Door Pair w/ Fixed Sidelites | 68 |  |  | Machined
GRAULICH | D18 | Living/Dining | Swing Door Pair w/ Fixed Sidelites | 84 |  |  | Machined
GRAULICH | D17 | Living/Dining | Swing Door Pair w/ Fixed Sidelites | 84 |  |  | Machined
GRAULICH | D16 | Living/Dining | Swing Door Pair w/ Fixed Sidelites | 84 |  |  | Machined